## DCT Platform
| Ideal Timing |  | Downstream Impact |  |  | Who DOES the work?
Category / sub-category | Site Feasibility/ Selection | Investigator Mtg /Site Activation | Site Budget | Site Resources | Site Activation Timeline | Responsible | Consulted | Informed | Informed | Informed
DCT Platform Card
What is the draft workflow and vendor plan for DCT methods across the study visits? (e.g eConsent, eCOA, etc) | X |  | X
How many technology platforms or systems will be used for the DCT elements of the study? | X |  | X | X
Is there a single portal for sites to access all the technology? ie one platform for all vendors and sites to use for the study? | X
Can sites use their own technology platforms? For which elements? | X |  | X | X
What is the data flow and transfer plan across the platforms / DCT data collection tools? | X |  | X | X
How many technology vendors will sites be expected to work with to use decentralized elements? |  | X | X | X
Do your vendors have the capability to integrate site technology with vendor tech platforms? e.g. scheduling tools / CTMS |  | X | X | X
What is the support strategy for each DCT / Technology Vendor? What are the hours and languages offered by the support team(s)? |  | X
How many tech platforms will study participants be expected to use for decentralized elements? |  | X
How will participant PII be protected and who will have access to it? |  | X
Can site use any of their qualified / validated DCT providers? | X
How many tech platforms will study participants be expected to use for decentralized elements? | X
In how many platforms will sites need to enter data manually? | X
How will participant PII be protected and who will have access to it? | X
What is the site responsibility for onboarding vendors involved in the DCT elements of the study? |  | X
Who is responsible to train the sites? |  | X
Who is responsible for supporting the site and the patient for each technology platform? |  | X
Who trains the study participants on the use of DCT tools / technologies? |  | X

## Training
| Ideal Timing |  | Downstream Impact |  |  | Who DOES the work? |  |  |  |  | Notes
Category / sub-category | Site Feasibility/ Selection | Investigator Mtg /Site Activation | Site Budget | Site Resources | Site Activation Timeline | Responsible | Consulted | Informed | Informed | Informed
Training and Support
How many technologies or other DCT provider offerings will sites need to be trained on?? | X
Is the training on-demand with a training credential (e.g. similar to EDC)? | X
Who needs to complete training at the site? (PI, SC, pharmacist, other?) | X
What format does each tech/ DCT provider use for training? e.g. video (duration?), in-app instructions, power point)? | X
In what format is training given? Inv meeting, self-training, Webex meeting? | X
What is the estimated total time the site needs to spend on training activities prior to site activation? | X
Is there a visit by visit infographic showing what is used, when and by who? (both patient and site staff)? | X
How are the patients trained on each DCT component? |  | X
How many DCT elements/ technology platforms will each patient need to be trained to use? |  | X
What is the site's role to train study participants on any DCT Elements and study-specific devices as part of the study start-up and study visits? |  | X
What training materials are available for direct-to-patient shipments? (IMP, equipment, other) |  | X
Are instructions sent to patients with DTP shipments? Or do sites share them with patients? |  | X
What training materials are available for training the patient on each DCT element? |  | X
What is the support model for site staff for each DCT element? |  | X
What is the support model for patients in the study for each DCT element and any study-specific device needs? What in-country support is used? |  | X
What is the escalation plan for support services if problems occur? |  | X

## Recruitment & Engagement
| Category / sub-category | Site Feasibility/ Site Selection | Investigator Mtg / Site Activation | Site Budget | Site Resources | Site Activation Timeline | Responsible | Consulted | Informed | Informed | Informed
Recruitment
High level | What is the patient engagement workflow, from awareness through study completion? Which Platforms are planned? | X |  |  | x
High level | Where are decentralized elements that intersect with patient engagement outlined in the study documents? | x |  |  | x
High level | Are there multiple locations for patient recruitment in the study? Are they physical or remote? | X |  | x | x
High level | Will sites be expected to recruit outside the site practice? | X |  | x | x | x
High Level | Who manages patient payments and using which reimbursement tools? |  | X | x | X
High level | What is the patient engagement workflow, from awareness through study completion? Which Platforms are planned? |  | X | x | X
Site Level | Is the online screening tool provided through a vendor? | X |  | x | x
Site level | Who is accountable to oversee patient eligibility for digitially recruited patients? | X |  | x | x
Site level | Are there special patient communication / engagement needs that will require extra site time? | X |  | X | X
Site level | Who follows up with patients to complete on-line screening and enrollement? |  | X
Site level | Who directs the patient to the on-line screening tool? |  | X
Site level | What is the expectation of sites to manage patient screening and enrollment? |  | X
Site level | Who manages patients to payments directly? |  | X
Site level | What is expected of sites to manage patient communication / engagement? |  | X

## eConsent
|  | Ideal Timing |  | Downstream Impact |  |  | Who DOES the work? |  |  |  |  | Notes
| Category / sub-category | Site Feasibility/ Selection | Investigator Mtg /Site Activation | Site Budget | Site Resources | Site Activation Timeline | Responsible | Consulted | Informed | Informed | Informed
Consent
High Level | Can sites use their own eConsent solutions? | X |  | x
High Level | Please explain the end to end workflow for use of eConsent. 1. Who sets up the patient? 2. Who manages amendments? 3. How is remote consent managed? | X
High Level | How is the site supported when end-users have questions? What are the support team's hours, languages and response times? | X |  |  | x
High Level | What is the eConsent workflow when a paper copy of the ICF is signed? (Upload capability?) | X |  |  | x
High Level | How will the site staff eConsent training be completed and documented? |  | X
High Level | How will sites be provided a copy of the signed ICF for long-term archiving? |  | X
High Level | Clarify the minimum device hardware and software requirements for eConsent. I.e. Phone model and software |  | X
Site Level | Is consent managed remotely? If so, what is the workflow? | X
Site Level | Will eConsent tool allow for source documentation notes within platform, or will site need to document notes separately? | X |  |  | x
Site Level | Does the eConsent tool use video or other media to support the consent process? | X |  |  | x
Site Level | Is the site responsible to confirm that the patient's device meets minimum eConsent platform requirements? |  | X

## Home Nursing
|  | Ideal Timing |  |  |  | Who DOES the work?
| Category / sub-category | Site Feasibility/ Selection | Investigator Mtg /Site Activation | Site Resources | Site Activation Timeline | Responsible | Consulted | Informed | Informed | Informed
Home Health Care
High Level | What's the overall workflow for home nursing? Which visits, which assessments? | X
High Level | Is in-home / mobile nursing an option in this study? If so, can patients decide to use it on a visit to visit basis? | X
High Level | Has a central in home nursing supplier been selected? | X
High Level | If in-home nursing is used, can it be managed by the site's preferred home nursing process / supplier? |  | X
High Level | What is the window for patients to decide on home health before the visit date? |  | X
Site Level | How is data collected from the in-home visit? Is an eSource platform used? | X
Site Level | Is there any need for telephone / telemedicine link to the in-home nurse during the visit? | X
Site Level | Is there any specific safety monitoring expected for in-home collected data? |  | X
Site Level | How is the nurse connected with the site staff? What process is in place to ensure the PI / staff approve the individual? |  | X
Site Level | How are in-home visits scheduled? by whom? Is this automated? How long prior to the visit must they be scheudled? |  | X
Site Level | Who provisions in specific supplies and to whom (Patient, site, HCP?) |  | X
Site Level | Where is operational data visible? To whom? |  | X
Site Level | Where is assessment data visible? To whom? |  | X
Site Level | What is the data management process for queries? |  | X

## BioSpecimen Collection
|  | Ideal Timing |  | Downstream Impact |  |  | Who DOES the work?
| Category / sub-category | Site Feasibility/ Selection | Investigator Mtg /Site Activation | Site Budget | Site Resources | Site Activation Timeline | Responsible | Consulted | Informed | Informed | Informed
Biospecimen Collection
High Level | What is the planned workflow for biospecimen collection? Are any central labs / imaging facilities planned? | X |  | X
High Level | Can patients have biospecimens / images collected at local lab facilities? | X |  | X | X
High Level | Are there specific vendors/ providers that may be used? |  | X
High Level | How is payment to for these services managed? Is this a pass through from sites? |  | X | X | X
Site Level | Who schedules appointments for the patient at the local faciliity? |  | X | X | X
Site Level | if a procedure needs to be rescheduled or repeated, who manages this? |  | X | X | X
Site Level | Who enters data from the biospecimen collection? Where is it entered? |  | X | X | X
Site Level | Where is the operational data from the visits visible? to whom? |  | X
Site Level | Where are the clinical results from the visits visible? To whom? |  | X

## DTP IMP
| Category / sub-category | Site Feasibility/ Selection | Investigator Mtg /Site Activation | Site Budget | Site Resources | Site Activation Timeline | Responsible | Consulted | Informed | Informed | Informed
IMP Medication Delivery
| Is Direct to Patient shipment of IMP used in this study? | X
High level | What is the workflow for DTP shipments? What is the end to end process? | X
High level | If DTP is used is delivery from site to patient or depot to patient? | X
High level | Is the courier/ delivery service provider familiar with clinical trial requirements? (PII protection, documentation). | X
High level | Are supplies sent direct to patient? e.g. Kits, medication admin supplies, devices? | X
High Level | How and where is drug accountability managed? |  | X | x | X
High level | How are patients trained on storage and administration of IMP? |  | X | x | X
Site Level | What role does the patient play in IMP drug accountability? |  | X | x | x
Site level | How is the patient trained about IMP drug accountability? |  | X | x | x
Site level | How is temperature control of IMP monitored? During shiptment? After delivery? |  | X | X | X
Site level | Where is temperature excursion data monitored and by whom? |  | X
Site level |  |  | X
Site level | How are temperature excursions managed? (Process and communication) |  | X
Site level | Who is accountable to manage temp excursions? |  | X
Site level | What is the support model for sites? For patients? | X
| How are patients trained on the IMP shipment and receipt processes? | X
| How are patients trained on the shipment and receipt processes for any other supplies? | X
| What is Site's role in the IMP chain of custody? | X
| What is expected of the pharmacy at my site? |  | X
| How are shipments scheduled? |  | X
| How is PII protected across the shipment / delivery process? |  | X
| How is IMP delivery confirmed? To Patient / By Patient? |  | X
| How is operational data re shipments managed? Who resolves issues? |  | X

## ePRO eCOA
|  | Ideal Timing |  | Downstream Impact |  |  | Who DOES the work?
| Category / sub-category | Site Feasibility/ Selection | Investigator Mtg /Site Activation | Site Budget | Site Resources | Site Activation Timeline | Responsible | Consulted | Informed | Informed | Informed | Notes
eCOA / ePROs
High Level | Can sites choose their own eCOA / ePRO platform and vendor? | X
High Level | What is required to collect ePROs/ eCOAs based on assessments/ scales used. (e.g. home health HCP, Video) | X |  | x | x
High Level | Does ePRO/eCOA have or need video upload capabilities? | X
High Level | Are all eCOA/s ePROs collected using Sponsor-defined technology? | X |  | x | x
High Level | Can site use their own video visit platform for video assessments? | X |  | x | x
High Level | What are requirements for patient's devices? Is Sponsor provisioning? | X
High Level | Who trains Site satff on eCOA/ ePRO platform / Tools? |  | X
High Level | Who acquires scales to be used in ePRO/eCOA? |  | X
Site Level | Has my site worked with this vendor before? |  | X
Site Level | Which roles and how many people need to be trained on eCOA / ePRO platform/ tools? |  | X
Site Level | Who trains patients? |  | X
Site Level | Who reviews data? Where is data stored/ reviewed? |  | X
Site Level | Do I understand the workflow and team roles to conduct ePRO / eCOA? |  | X
Site Level | Are there home health visits where ePRO/eCOA is performed? Are site personnel involved? |  | X
Site Level | Who creates patient training mateirals? |  | X
Site Level | Who provides tech support for patients? |  | X
Site Level | Who confirms patient's tech device meets the eCOA / ePRO requirements? |  | X

## DTP Supplies
|  | Ideal Timing |  | Downstream Impact |  |  | Who DOES the work? |  |  |  |  | Notes
| Category / sub-category | Site Feasibility/ Selection | Investigator Mtg /Site Activation | Site Budget | Site Resources | Site Activation Timeline | Responsible | Consulted | Informed | Informed | Informed
Pharmacy / Equipment (non-Wearables)
HIgh Level | Is Direct to Patient shipment of IMP used in this study? | X
High Level | If DTP IMP shipment is used, is it from site to patient? or from depot to patient? | X
HIgh Level | Are supplies (e.g. lab kits, weight scales, study supplies) sent direct to patient? | X
Site Level | How are shipments scheduled? |  | X | X | X
Site Level | Who schedules shipments? |  | X
Site Level | How is temp control monitored? |  | X
Site Level | Who is accountable to manage temp excursions? |  | X |  | X
Site Level | How is delivery confirmed? |  | X |  | X

## Wearables DHT
|  | Ideal Timing |  | Downstream Impact |  |  | Who DOES the work?
| Category / sub-category | Site Feasibility/ Selection | Investigator Mtg/ Site Activation | Site Budget | Site Resources | Site Activation Timeline | Responsible | Consulted | Informed | Informed | Informed
Digital Health Tools (DHT) - Wearables and Devices
High Level | What is the DHT / Device workflow across the study visits? How is the DHT data used? | X |  | X | X | [6 empty] | NOTE: In rare cases, the DCT vendor may act as the DHT / Other vendor.
High Level | Who provisions DHTs to Patients? (Wearabes / Sensors) | X |  |  | X | X
High Level | Can patients use their own device? (BYOD approach) | X
High Level | Is there financial support for patients to cover data plans / wfi access? | X |  |  | X
High Level | Who trains patients when BYOD DHT devices are used for data capture? | X |  |  | X
High Level | What is the end to end plan for DHT use / data collection in the study? |  | X | X | X
High Level | Who maanges patient costs for data plans / wifi access? |  | X | X
High Level | Who confirms a patient's device meets BYOD requirements? |  | X | X | X
High Level | Where is device data collected visible? To whom? |  | X
High Level | Where is Operational data collected by DHTs visible? To whom? |  | X | X | X
Site Level | Does site provision DHT devices? | X |  |  | X
Site Level | Who trains study site staff on DHT device use? | X |  | X | X
Site Level | Who supports patient questions re DHT devices? | X |  | X | X
Site Level | Who trains patients on use of DHT devices? | X |  | X | X
Site Level | Who ensures patients have access to Wifi/ Cellular networks? |  | X |  | X | X
Site Level | Who deploys a working device to a patient if a DHT device fails? |  | X | X | X
Site Level | When are patients trained on use of DHT devices? |  | X
Site Level | Who reviews data collected by DHTs for completeness? |  | X
Site Level | Who reviews data collected by DHTs for safety signals? |  | X
Site Level | Who is accountable to review data queries based on DHT data? |  | X

## Definitions
Milestone | Ideal Timeframe
Feasibility | >6 months before Site Initation
Site Selection | >3 months before Site initaiton
Investigator Meeting | May serve as Site Initiaton for some indications
Site initiation to activation | <1 month between initiation to activation/ Ready to enroll
First Patient Screened | <1 week from Activation/ Ready to enroll
Is Initiaton the same as Activation/ Ready to Enroll?
Technology | Software and/or hardware enabled solutions. Could be a point solution
Platform | Integrated service offering. Typically more than a single solution supported.
Services | Resource supported servives

## Stakeholder List
Site
CRO
DCT Vendor
Other Vendor
Sponsor
Patient

## Original Tasks and Roles
|  | Ideal Timing |  | Downstream Impact |  |  | Primary Responsibility |  |  |  |  | Notes
| Category / sub-category | Site Feasibility/ Selection (Preference) | Investigator Mtg /Site Activation | Site Budget | Site Resources | Site Activation Timeline | Site | Sponsor | CRO | DCT Vendors | Other Vendors
Platform
SSU | Is there a single platform that will support all the DCT elements? ie one platform for all vendors and sites to use for the study? | x | study start up |  |  |  | I | A | C | R | R | Depends on complexity of study design, Infrastructure, capabilities, access, timeline involved
SSU | How many technology platforms or systems are involved in implementing the decentralized components of the study? |  | x |  |  |  | I | A | R | C | C/I
SSU | How many technology vendors will your site be expected to work with to implement decentralized components? | [5 empty] | I | A | R | I | I
SSU | Are the technologies being used for decentralized components single sign-on (SSO) enabled? |  | X |  |  |  | I | R? | R? | A? | C
EX | What is the role of your site in onboarding vendors involved with this study? |  | X |  |  |  | x | x |  |  |  | Decision questions: will vendors be interacting with Patients or study teams, Do the vendors need access to site internal systems? Will vendors be providing data back to the site or sponsor?
| How many technology vendors will study participants be expected to work with to use decentralized components? | [5 empty] | I | A | R | C | C
EX | Will the site have access to a support desk help for each of the technology platforms needed to implement the study? | [5 empty] | I | A | C | R | R
Is it possible to intergrate the sponsor platform into existing site platforms?
What decentralized capabilities are qualified / study ready at your site Is there any opportunity to utilize those capabilities instead of sponsor provided technology? (Site BYOT)
Technology
SSU | If there are external technology vendors involved in the study to help implement the study’s decentralized components, have the vendors been identified and are their roles and responsibilities clearly stated/outlined? | x |  |  |  |  | I | A | C | R | C | Site needs to have access to vendor quality control processes, understanding of vendor R&R, Sponsor needs define the strategy for any specific tech that's new and ensuring it's set up for the trial.
SSU | Do the decentralized components outlined in the study protocol require other external groups / vendors to manage patients in the study (e.g., patient concierge, patient recruitment support, patient payment vendor)? | X |  |  |  |  | I | A | R | C | C/I | As early as possible. ideally included in protocol synopsis for comment.
EX | Device Provisioning: If the study includes or requires a digital health device such as a sensor or wearable, will the device be sent directly to study participants from the sponsor or CRO, or is your site involved in device provisioning (e.g., time/effort/cost to ship devices)?
SSU | Can patients use BYOD for the study? do patients need to be given a device? What is that process? |  | X |  |  |  | I | A | R | C | R | The Sponsor will need to determine which device is aprpopriate for use and what software version is acceptable. The provision vendor will have a reponsitibility to send, set up and train the provisioned device
| if BYOD, how is the patient's device compatible? What if there is no wifi / cell access? |  | X |  |  |  | I | A | I | R | I | Sponsor will need to determine what's acceptable based on input from DCT / vendor.
EX | If the study is allowing patients to use their own digital device in a BYOD environment, will your site be expected to provide training for study participants and to set up their devices?
Tiffany | eCOA / ePROs
SSU | Has your site worked with the study’s eCOA system previously? If not, will staff need training? | x |  |  |  |  | responsible for making staff available for training | responsible for providing training and reference material and providing support
SSU | What roles and how many people need to be trained in the eCOA system?
EX | Based on the decentralized components identified for the study, what is required for collecting ePROs?
EX | Will patients require training on the ePro(s) used? |  | x |  |  |  |  | x
Wearables
SSU | If patients have an acceptable wearable, can they use their own? (BYOD) | x | [5 empty] | x
SSU | Is there any support for patients to cover costs for data plans / wifi access? Who manages this?
SSU | Who provisions devices? | [6 empty] | x
EX | When are patients trained on the use of devices? By whom?
EX | If a device fails, who is accountable to ensure a working device is deployed? Set up?
EX | What is the support model for patients (in home)? |  | X
EX | What is the support model f(Training / Help Desk) or study staff (on site)? |  | X
EX | What are the expectations of data monitoring by site staff for wearable data? |  | X
EX | Are there any specific safety oversight expectations related to wearable data? |  | X
EX | Where is the data tracked by wearables visible? To whom? |  | X
EX | Are there any data management expectations for data generated from wearables? |  | X
SSU | How many technology platforms or systems are involved in implementing the decentralized components of the study?
SSU | Is there a single platform that will support all the DCT elements? ie one platform for all vendors and sites to use for the study? | x | study start up |  |  |  |  | x (ensuring the infrastruce and capabilites, staff, training availability, etc) | x | x | x | Depends on complexity of study design, Infrastructure, capabilities, access, timeline involved
SSU | Are the technologies being used for decentralized components single sign-on (SSO) enabled?
SSU | How many technology vendors will your site be expected to work with to implement decentralized components?
EX | Will the site have access to a support desk help for each of the technology platforms needed to implement the study?
EX | Device Provisioning: If the study includes or requires a digital health device such as a sensor or wearable, will the device be sent directly to study participants from the sponsor or CRO, or is your site involved in device provisioning (e.g., time/effort/cost to ship devices)?
EX | If the study is allowing patients to use their own digital device in a BYOD environment, will your site be expected to provide training for study participants and to set up their devices?
Becky | Logistics
1 | Central or site selected vendor? | feasibilty
| Central | feasibilty |  | N | N |  | I | A | R | CI | C | DCT vendor consulted during pre-award phase of vendor selection
| Site & Central (flexibility) | feasibilty |  | Y | Y |  | R | AC | C | I | I
2 | Does this PI have input into vendor selection? Is there flexiblity to choose a vendor? | feasibilty |  |  |  |  | R | AC | C | I | I
3 | How will these tasks be managed during study conduct? Through a dashboard, single platform, separate systems? Single sign on for the study? | SIV
4 | PI Oversight | Pre study visit
5 | How is my Patient's PHI Data protected? | Pre study visit |  |  |  |  | R | A | CI | R | R
5 | What is the data flow ( to and from the vendor, regarding PHI, other related data)
6 | What is the expectation for data management / data oversight/ safety events?
7 | How are patients supported in navigating appointments / ensuring high customer service / etc? (patient point of contact)
Who is accountable for resolving missing data? Would apply to all logistic related
How is payment for services managed? How is site effort reimbursed?
Will your system allow integration into site systems? (e h r, CTMS)
Who is responsible for scheduling services or appointments through the vendor?
| Who will need training to support vended activities? Who will need to be trained (roles) and how much time will it take? |  | X
Biospecimen / image collection
SSU | Can patients have biospecimens / images collected at local lab facilities? | X |  | X |  |  | I
EX | If so, are there any specific facilities / providers that may be used? How is payment for these services managed? |  | X | X | X |  | I | A | R | CI | CI
EX | How are appointments scheduled? By whom? how long prior to the expected visit date? |  | X | X | X |  | I | A | R | C | C
EX | How is data from the visit collected? By whom? How is it entered to the clinical data set? |  | X | X | X |  | I | A | R | CI | C
EX | if a procedure needs to be rescheduled or repeated, who manages this? |  | X | X | X |  | I | A |  | CI | C
EX | Where is the data from the visits visible? to whom? |  | X | X | X |  |  | A |  | CI | R
Pharmacy / Equipment (non-Wearables)
EX | Is Direct to Patient shipment used in this study?
EX | If DTP is used, is it from site to patient? or from depot to patient?
EX | How are shipments scheduled? by whom?
EX | How is temp control monitored? Who is accountable to manage temp excursions?
EX | How is delivery confirmed? By whom?
Adrian | In home nursing
SSU | Is in-home / mobile nursing in the study protocol? | X |  | X | X |  | CI | A | R | C | I | Sponsors and CROs are traditionally the stakeholders that make the decision around inclusion of the service in a study protocol. In line with the site voice in protocol development workstream for this CoLab, i have added consulted to the site column, along with sites being informed as not all sites will be consulted during protocol development. The HHC vendor should also be consulted on the feasibility of service based on the SOA and country mix and will be able to advise the CRO/Sponsor as to which visits are and are not feasible, along with potential adjustments to ease the site and patient burden related to the protocol, without impacting safety and efficacy
| Will the service be mandatory or optional for patients and/or sites? | X |  | X | X | X | CI | A | R | C | I | Sponsors and CROs are traditionally the stakeholders that make the decision around whether the service will be mandatory or optional and how this is included in the study protocol. In line with the site voice in protocol development workstream for this CoLab, i have added consulted to the site column, along with sites being informed as not all sites will be consulted during protocol development. The HHC vendor should also be consulted on the feasibility of service based on the SOA and country mix and will be able to advise the CRO/Sponsor as to which visits are and are not feasible, along with potential adjustments to ease the site and patient burden related to the protocol, without impacting safety and efficacy
| Will patients be able to decide which visits they use the service on? |  | X |  |  |  | CI | A | R | C | I | Where the service is optional, the ultimate decision should rest with the patient, although sites will always have a view on this and answers to other questions may direct once the site approaches activation and implementation. However in general terms, if option in the protocol, the answer would be Yes
SSU | Has a central in home nursing supplier been selected? | X |  | X | X | X | CI | AR | CR | I | I | This should be a decision taken by the Sponsor in consultation with a site advocacy or protocol review group and may need to consider whether the majority of sites have a site preferred HHC supplier and consideration should be given to offering a combination of central and site preferred to make the service more accessible for all sites. this may bring challenges for Sponsor/CRO in ensuring process management alignement with the protocol alongside the sites and may also increase the capacity required by site to manage this. many private single site organizations are unlikely to be able to effectively qualify and select a preferred supplier and this may burden the sposnor and CRO if qualification support is required to be provided to site
SSU | If so, how is the nurse connected with the site staff? What process is in place to ensure the PI / staff approve the individual? |  | X |  | X | X | C | A | C | R | I | This will vary by HHC supplier and their SOPs. this should be considered early in the process but it is key to consult with sites in the lead up to Study-service-specific process document finalization. have sites involved in review and agreement on the overall process that demonstrates efficiency for sites and supports effective PI oversight
SSU | If in-home nursing is used, can it be managed by the site's preferred home nursing supplier? | X |  | X | X | X | C | A | CI | I | I | See comments for central home nursing vendor section
EX | How are in-home visits scheduled? by whom? Is this automated? How long prior to the visit must they be scrheudled? |  | X |  | X |  | CI | C | CI | A | I | This will vary by HHC supplier and their SOPs. this should be considered early in the process but it is key to consult with sites in the lead up to Study-service-specific process document finalization. have sites involved in review and agreement on the overall process that demonstrates efficiency for sites and supports effective PI oversight
EX | Is there any need for telephone / telemedicine link to the in-home nurse during the visit? | X |  | X | X |  | CI | AR | CR | C | I | This would be something that should be determined alongside protocol development as discussed in the notes for inclusion of the service in the protocol
EX | How is data collected from the in-home visit? Is an eSource platform used? |  | X |  | X |  | CI | A | CI | RC | CI | Realtime access to eSource by both Site and DCT vendor vs offline eSource with provision of true copies to site by DCT vendor. DCT vendor alignment with eSource vendor vs DCT vendor with inhouse eSource platform | Does the system provide realtime access to the sites when the nusre enters data in the home? What happens when there is no signal to upload the data in realtime. If the system operates offline how does site get the data and who is responsible for entering the data into the EDC? If paper source is being used what is the process for providing this to the site? do the worksheets capture all relevant data points needed by the site and sponsor? | I have worked with a couple of different eSource systems. 1st is an inhouse system that operates offline and negates the need for a signal to transmit the data in realtime, and is a bespoke mobile application that the Nurses utilize. Using this system the vendor coordinator would Quality check the data and send a true copy of the data along with QC audit trail to the site as a pdf via email. initially sites had to transcribe the data into the EDC but as the system developed, intergrations with other EDC systems were implemented to ensure auto uploads of the data on a regular basis. the 2nd system was a 3rd party system that served as eSource for all sites and in-home nurses. data was entered and visible to all stakeholders in realtime, alongside the audit trail. both systems had their merits and downfalls for all stakeholders but were effective
EX | How is the data from the in-home visit entered to the clinical database? |  | X |  | X |  | CI | A | C | R | CI | This will vary by Source type (paper versus electronic), HHC supplier and their SOPs and any other vendors that this may impact. this should be considered early in the process but it is key to consult with sites in the lead up to Study-service-specific process document finalization. have sites involved in review and agreement on the overall process that demonstrates efficiency for sites and supports effective PI oversight
EX | Is there any specific safety monitoring expected for in-home collected data? |  | X |  | X |  | CI | A | R | C | CI | This should be considered early in the process, by the sponsor and CRO and it is vital to to consult with the HHC supplier, sites & other safety monitoring vendors, in the lead up to Study-service-specific process document finalization. have sites involved in review and agreement on the overall process that demonstrates efficiency for sites and supports effective PI oversight
Regulatory
Alexa | IRB
SSU | Who is accountable for IRB submissions / respondingi to questions from IRB re DCT elements? |  | X | X: X; C: R; CI: R/A
SSU | Who creates the IRB content for any DCT-specific submission needs (e.g. screenshots / wireframes) |  | X |  | X |  | A | CI | A | R
SSU | If the site has a local IRB, is it acceptable to use a study-wide central IRB submission? |  | X | X: X; C: A; A: CI; CI: R
FDA - anticipate an update this year focused on examples
CMS
Becky | Financial
Budgets
Invoicing
Billing
Jane/Seema | Data
accountablity / validity
EX | Who is accountable to follow up on missing patient-generated data?
Ownership
Storage
SSU | How long will data be needed to be stored?
SSU | Where will the data be stored? Is the sponsor providing financial support for storage?
Management
Patient Engagement
SSU | Are the decentralized components that intersect with patient engagement clearly outlined in the study? |  | X |  | x |  | I | A | R | C
SSU | Recruitment |  |  | C: I; A: A; CI: R; I: R
SSU | Is the online screening tool provided through a vendor? | x | bar: C to A; I
SSU | Is your site involved in directing the patient to the online screening tool? |  | x | X: x; C: I; A: A; I: A/R
EX | What is expected of the site for management and/or follow up? |  | x | bar: A
EX | Who is accountable to over see patient eligibility if the patient is recruited digitally? | X |  | C: A/R; A: A; CI: C
SSU | Are there multiple locations for patients in this study? E.g. are patients located in multiple states or regions? | x |  |  |  |  | I | A | R | C | C
SSU | Have these been clearly ID'd? Are we recruiting patients outside the clinical site practice and if so, how? | X |  | x | X |  | I | A | R | C | C
EX | What is the expectation at the site level for managing pt communication, engagement, and study implementation? |  | x | X | X |  | C | A | R | C | R
EX | Based on the inclusion/exclusion criteria, are there special considerations for patient communication and/or engagement that would require additional site staff training or staff time? |  | X | X: x; X: X; C: R; A: A
Caroline | Training / Support
SSU | Will your site be responsible for training study participants on the study-specific device as part of the study start-up and study visits?
EX | Has your site been provided materials to educate and engage study patients on the technology or device or are you responsible for educating/training the patient?
EX | Will the site serve as a support desk function for the study participants to assist them with the use of the study device?
Marina | Consent
SSU | Is consent managed remotely? in person? Or either?
EX | What role is expected of the PI if the consent process is managed remotely?
EX | If eConsent is used, how are patient questions documented? Is there an esource capture for questions?
EX | Does the eConsent tool use video or other media to support the consent process?
EX | Does the eConsent tool track the version the patient signed and how it aligns to local consent revisions?
Jenn | PATIENT PAYMENTS
EX | Is your site expected to manage patient payments? If so, how, and what patient reimbursement tools are used? |  | X
EX | Is your site expected to work with a patient concierge to help manage payments? |  | X
Note on B2: ====== ID#AAABX1ikbzA tc={6C06F7FC-487F-4370-99A5-154E49600BA9} (2024-10-28 16:25:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Consider whether questions apply to across all DCT methods? Or if they need to be included in each specific method.
Note on B3: ====== ID#AAABX1ikb0c tc={D8738FCD-C7B7-4CF0-8600-8A5606CB44EC} (2024-10-28 16:25:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Move this to technology category
Note on B6: ====== ID#AAABX1ikbzs tc={EC2FF939-3E1B-493B-87A0-EFC2BB293409} (2024-10-28 16:25:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is this the same as How many platforms / systems are involved in implementing the DCT components?
Note on B8: ====== ID#AAABX1ikb0I tc={B1A385EF-D45C-4F0A-A290-7DFEDC9A92FA} (2024-10-28 16:25:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add this question to each vendor type / DCT solution.
Note on B12: ====== ID#AAABX1ikb0s tc={7864482D-3170-4643-8990-41B365F13167} (2024-10-28 16:25:39) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is really the scope of the BYOT team that's in progress - Do you think this is helpful for us?
Note on B14: ====== ID#AAABX1ikbyQ tc={1774D352-D8B6-4F4C-ADE1-9836630C9F38} (2024-10-28 16:25:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Similar to first question? Ask Caroline for clarification
Note on B26: ====== ID#AAABX1ikb1I tc={9734CA69-3156-4E28-8F45-A0771DB0895A} (2024-10-28 16:25:39) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Has the assigned staff for the study worked in this platform? If not, who will do the training for these resources?
Note on B127: ====== ID#AAABX1ikb1Q tc={53DCF4BF-77DF-4319-97F8-7C828A628EAF} (2024-10-28 16:25:39) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: May be integrated into other sections. Add anything needed
Note on B135: ====== ID#AAABX1ikb1E tc={4FBB8E67-5FF9-4886-B5D5-B9C5E449D197} (2024-10-28 16:25:39) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Isn't the PI / Delegated individual always accountable?
Note on B139: ====== ID#AAABX1ikbyA tc={164357CA-9320-460D-B9C3-86E89773E7BE} (2024-10-28 16:25:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I could use an example to better understand this.
Note on C14: ====== ID#AAABX1ikb08 tc={97C71436-F8C8-4A28-BC67-9E8FF0D10D89} (2024-10-28 16:25:39) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ideally 6 months pre site activation
Note on C17: ====== ID#AAABX1ikb04 tc={4EF8586C-909B-4E5A-8B0A-E2E068546B16} (2024-10-28 16:25:39) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ideally 6 months pre site activation
Note on C18: ====== ID#AAABX1ikbyk tc={29CD6370-861D-424E-9B6E-E6130C943830} (2024-10-28 16:25:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ideally 6 months pre site activation
Note on D17: ====== ID#AAABX1ikb0k tc={E6205038-8725-4226-B266-C0F899D73302} (2024-10-28 16:25:38) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vendor would traing sites. Sites train patients at the time of enrollment. Help desk support is mandatory